## BackLog
# | Type | Description | Image (Refer Sheet) | Samples Path | Sample File Name | Status | Adlib's Response
BL-1 | Bug | When File with same name already exists in temp folder, File not processed and exception occurred. | BL_1 |  |  | JB Tested | This should be resolved now
BL-2 | Bug | When file size is too big, only files are moved to temporary folder. Searchable PDFs and PDFInfo files were not created. Even there is no information in error log. |  | /Samples/20160817/ | MyDictionary.pdf | JB Tested | All samples test OK in my environment now.
BL-3 | Bug | For some pdf files, Searchable PDFs were not created. Even there is no information in error log. Try all files in samples path. |  | /Samples/20160715/ | All files | JB Tested | All samples test OK in my environment now.
BL-4 | Query | How to find whether any given file is completely processed or not? |  |  |  | Closed | If there are files left in the TEMP folder, that is one sign, the definitive answer will be the Adlib UI for the OCR Job status as well as if there is a respective PDFInfo for that file in the reports folder
BL-5 | Change | Change delimiter in TagIndex.txt from tab to comma |  |  |  | JB Tested | Commas it is...
BL-6 | Query | How to find whether any given file is completely processed or not? |  |  |  | Closed | Same as BL-4 ;-)
BL-7 | Bug | When a file is processed second time after deleting the files from Temp, SearchablePDF and PDFInfo folders. File was not processed again, only the files were copied to temp folder. Do we have any limitation in processing the same file again? |  |  | Any file | JB Tested | All samples test OK in my environment now, even with multiple runs.
BL-8 | Query | When any exception occurred like "BL-1" above, I think TagExtractor is not at all working. Only files were created in temp folder. I think it was by Adlib main software. The issues 2 and 7 may be because of the above exception. Now I am not sure how to reset. TagExtractor is not working even after deleting all the files in Report folder and temp folder. Even I restarted it. |  |  |  | JB Tested | All samples test OK in my environment now.
BL-9 | Bug | Process not stopped even after placing an empty (0-byte file) in the Input directory with the filename stop |  |  |  | JB Tested
BL-10 | Query | On what size the file TagIndex.txt shall be rolled out. Is it 1MB or 2MB. I could not check it now because of BL-8. |  |  |  | JB Tested | This is now configurable, please make sure you are using an updated configuration file included with the August 31st Build.
BL-11 | Query | Can we add a flag in "JTTemplate.xml" to enable/disable of removing blank spaces in a string before finding the match? We found some tags are with white spaces. |  |  |  | Open | We expect the Usser Dictionary will resolve this.
BL-12 | Bug | Some files in temp folder are not deleted or moved |  |  |  | JB Tested | This was due at least partially to timing. The trigger is the PDFInfo but the Searchable PDF may not have been there. There is now a 5x attempt to move/delete and a 5-second delay for each attempt meaning we'll wait up to 25 seconds after the PDFInfo appears to move the Original and Searchable PDF for each rotation.
BL-13 | Bug | Threads would not exit when a collection of files or folders were being processed. |  |  |  | JB Tested